## Sheet1
Instructions: 1. Select one of the available status for each task. 2. If you decided on which of your teammate is going to work on a particular task, the status should be changed to "Assigned" and that student's name should be entered under "Assigned To". 3. After you start working on a task, change the status to "In Progress". Once it's completed, the status should be "Completed". If it can't be completed because of an issue, the staus should be "Blocked" and comment on why it's blocked. 4. Select expected start dates and end dates for every task. 5. Update the actual start date and end date of your tasks regularly.
Task | Status | Assigned To | Exp. Start Date | Exp. End Date | Actual Start Date | Actual End Date | Comments
Redo Arduino-MySQL API in C Python | Completed | Jonathan W. & Joel C. | 2018-04-12 | 2018-04-21 | 2018-04-12 | 2018-04-28
"Improve PHP-MySQL API | Completed | Jonathan Westerfield | 2018-04-12 | 2018-04-17 | 2018-04-12 | 2018-04-22
Convert Arduino/Python to pure Arduino | Completed | Joel Coatney | 2018-04-10 | 2018-04-26 | 2018-04-10 | 2018-04-30
Redo the web interface | Completed | Jonathan Beechner | 2018-04-17 | 2018-04-27 | 2018-04-22 | 2018-04-28
Document Improvements to PHP API | Completed | Jonathan Westerfield | 2018-04-23 | 2018-04-28 | 2018-04-27 | 2018-05-02
Document Improvements to Python-MySQL API | Completed | Jonathan Westerfield | 2018-04-23 | 2018-04-28 | 2018-04-27 | 2018-05-02
Put a linear regression on the graph | Completed | Jonathan Beechner | 2018-04-24 | 2018-04-28 | 2018-04-27 | 2018-04-30
Document Improvements to web interface | Completed | Jonathan Beechner | 2018-04-24 | 2018-04-28 | 2018-04-28 | 2018-05-02
Document Improvements to Arduino | Completed | Joel Coatney | 2018-04-24 | 2018-04-30 | 2018-04-24 | 2018-04-30
Repackage code for submission | Completed | Jonathan Westerfield | 2018-04-30 | 2018-05-03 | 2018-05-02 | 2018-05-02